SATMIX MOBILE APP DEVELOPMENT & STORE LAUNCH

Conservative Production Engineering Roadmap, Delay Vectors & Multi-Store Release Blueprint

| Target Product: Satmix Mobile App v1.0 (iOS & Android / React Native Expo EAS) | Conservative Horizon: 14 Weeks (3.5 Months) — Includes External Banking, VAPT & Store Buffers |
| --- | --- |
| Prepared By: Veer Khanna (Co-Founder & CTO) | Executive Review: Shashank Jajodia (CFO), Sheiden Borges (CEO) |

1. Executive Summary & Timeline Estimation Logic

For a regulated Indian fintech platform handling automated daily recurring UPI e-mandates, DigiLocker e-KYC, and non-custodial crypto basket accumulation, software engineering accounts for only ~55% of the total go-to-market timeline. The remaining 45% is governed by external banking approvals, CERT-In VAPT security remediation, and Apple/Google regulatory store reviews. To protect financial runway and avoid premature launch commitments, this document establishes a conservative 14-week baseline (~3.5 months).

| Timeline Phase / Milestone | Aggressive Velocity | Conservative Baseline (With Buffers) |
| --- | --- | --- |
| Phase 1: Architecture, Design Tokens & Biometric Auth | Weeks 1 – 2 (10 Days) | Weeks 1 – 2 (14 Days) |
| Phase 2: Dashboard, Dynamic Baskets & Compounding Simulator | Weeks 3 – 4 (12 Days) | Weeks 3 – 4 (14 Days) |
| Phase 3: Fintech Rails, UPI Autopay & DigiLocker e-KYC | Weeks 5 – 6 (12 Days) | Weeks 5 – 7 (21 Days) [+1 Wk Bank UAT Buffer] |
| Phase 4: Gamification, Retention & CERT-In VAPT Audit | Weeks 7 – 8 (12 Days) | Weeks 8 – 10 (21 Days) [+1.5 Wk Audit & Fixes] |
| Phase 5: Google 14-Day Closed Testing & Apple TestFlight | Week 9 (7 Days) | Weeks 11 – 12 (14 Days) [Strict 14-Day Rule] |
| Phase 6: Store Submissions, Guideline 3.1.5 & Public Go-Live | Week 10 (7 Days) | Weeks 13 – 14 (14 Days) [+1 Wk Apple Query Buffer] |

2. Detailed Phase-by-Phase Engineering Sprints

PHASE 1: Mobile Foundation, Design Tokens & Biometric Auth Shell (Weeks 1 – 2 (Days 1 – 14))

Core Objective: Build a production-hardened React Native Expo EAS application shell with biometric authentication and dynamic risk assessment onboarding.

Expo EAS Configuration: Managed workflow with custom native config plugins for biometric authentication, secure hardware storage, and push notifications.

Design Token Architecture: Native implementation of Satmix Dark (#08090F) and Light (#F4F6FB) color systems, typography scale, and 4pt layout grids.

Authentication Engine: Indian 10-digit mobile input with MSG91 SMS OTP verification and automated OTP autofill.

Security PIN & Biometrics: Custom 4-digit PIN lockpad with haptic feedback hooks (expo-haptics) and FaceID / TouchID / Fingerprint unlock (expo-local-authentication).

Dynamic Risk Assessment Quiz: 4-question risk profiling engine scoring users into 'Safe & Stable' (Low Risk) or 'Growth Strategy' (High Risk) portfolios in under 30 seconds.

Exit Milestone: Executable iOS & Android builds running smoothly on physical devices with complete onboarding, PIN authentication, and session persistence.

PHASE 2: Core Investor Dashboard, Dynamic Baskets & Compounding Simulator (Weeks 3 – 4 (Days 15 – 28))

Core Objective: Deliver all primary investor views, interactive charts, and dynamic financial calculations calibrated to CFO-approved basket allocations.

Live Portfolio Screen: High-performance portfolio balance display, P&L badge (+₹X / +Y%), active strategy card, and time-filter tabs (1W, 1M, 3M, 1Y, ALL).

60 FPS Native Charting: Canvas/SVG vector charts built with react-native-svg & Skia for smooth gesture scrubbing and dual trajectory comparisons.

Baskets & Strategy Engine: Dynamic allocation visualization for Low Risk (60% BTC, 30% ETH, 10% USDC) and High Risk (35% SOL, 25% AVAX, 25% DeFi, 15% BTC).

Interactive Micro-Savings Slider: Custom gesture-based slider (₹10 to ₹500/day) with instant daily, monthly, and multi-year compounding projections (1Y, 3Y, 5Y).

Live Crypto Price Feed: Resilient CoinGecko Pro API integration with background caching, offline data fallbacks, and live price tickers.

Exit Milestone: All core financial simulation and browsing screens fully interactive, styled to pixel-perfection, and synchronized with mathematical models.

PHASE 3: Fintech Rails: UPI Autopay e-Mandates, DigiLocker e-KYC & Bank Rails (Weeks 5 – 7 (Days 29 – 49) [Includes 1-Week Gateway UAT Buffer])

Core Objective: Integrate production payment SDKs, automate daily UPI debit mandates, and complete user identity verification infrastructure.

DigiLocker & Aadhaar e-KYC: Seamless SDK integration (Hyperverge/IDfy) for Aadhaar XML verification, PAN real-time validation, and anti-fraud liveness match.

UPI Autopay & E-Mandate Engine: Production integration with Cashfree/Razorpay AutoPay SDK with deep-linking across GPay, PhonePe, Paytm, BHIM, and Cred.

Daily Execution & Retry Daemon: Backend webhook listeners for mandate success/failure and automated smart retries for failed recurring debits.

Mandate Management UI: User controls to pause daily investments, change daily deposit amounts, or switch active portfolio strategies.

Bank Account Linking & Payouts: Penny-drop bank verification for instant IMPS/NEFT fiat withdrawal processing.

Exit Milestone: End-to-end sandbox and live UAT testing of real ₹10 UPI Autopay mandate registrations and successful KYC document verification.

PHASE 4: Gamification, Profile, Settings & CERT-In VAPT Security Clearance (Weeks 8 – 10 (Days 50 – 70) [Includes 2-Week VAPT Remediation Buffer])

Core Objective: Complete user retention loops, tax reporting, and undergo third-party security audits required for fintech and FIU compliance.

Streak & Gamification Engine: Daily savings habit counter (Gold Zap), XP tier progression (Lv.1 to Lv.4 Accumulator), and celebration confetti bursts.

Tax & Statement Reporting: Generation and export of official FY P&L tax statements in formatted PDF and CSV formats.

Push Notifications & Reminders: Firebase Cloud Messaging (FCM) integration for daily deposit confirmations, streak alerts, and market updates.

CERT-In Certified VAPT Audit: Comprehensive Dynamic (DAST) and Static (SAST) application penetration testing on both iOS and Android release builds.

Security Hardening & Remediation: Implement certificate pinning, API rate-limiting, encrypted token rotation, and SQL injection sanitization.

Exit Milestone: Official CERT-In VAPT Security Clearance Certificate issued; zero High or Critical vulnerabilities.

PHASE 5: Google Play 14-Day Closed Testing & Apple TestFlight Community Beta (Weeks 11 – 12 (Days 71 – 84))

Core Objective: Fulfill Google Play Console's mandatory 20-tester 14-day testing requirement and conduct a closed external beta with 100 early adopters.

Google Play 14-Day Closed Cohort: Maintain 20+ active opted-in testers across Android 10 through Android 15 devices for 14 continuous days.

Apple TestFlight External Beta: Distribute build to 100 community beta testers via TestFlight public link and gather crash telemetry via Sentry.

Performance & Memory Optimization: Profiling app cold-start times (<1.8s target), memory leak fixes, and network error handling under low-bandwidth connections.

Store Listing Assets & Metadata: Production 6.7" and 6.5" App Store screenshots, Google Play feature graphics (1024x500), localized descriptions, and FIU compliance URLs.

Exit Milestone: Completion of Google Play's 14-day closed testing prerequisite; zero unhandled crash reports across beta cohort.

PHASE 6: App Store & Google Play Review, Staging Cutover & Public Launch (Weeks 13 – 14 (Days 85 – 98) [Includes 1-Week Review Query Buffer])

Core Objective: Clear Apple Guideline 3.1.5 financial review, pass Google Play production checks, and execute public release.

Apple Financial Services Review: Submission under App Store Review Guideline 3.1.5 (Cryptocurrency / Fintech), providing FIU-IND registration documentation and test credentials.

Google Play Production Track Approval: Final submission of signed production Android App Bundle (.aab) with Target SDK 35 compliance.

Production Gateway Cutover: Switch all payment gateways, KYC APIs, and exchange liquidity rails from sandbox/UAT to live production credentials.

Launch Day Monitoring: Real-time Datadog/Sentry error alerting, Cloudflare DDoS monitoring, and founder on-call support.

Exit Milestone: Satmix Mobile App approved and publicly downloadable on the Apple App Store and Google Play Store.

3. Exhaustive Delay Vectors, Potential Impact & Mitigation Protocols

To provide institutional rigor for the CFO and executive team, the following matrix identifies the 6 specific friction points that could introduce latency, the potential time slip if unmanaged, and the concrete technical/operational mitigation protocols Satmix has established.

| Delay Vector | Root Cause / Trigger | Potential Delay Impact | Probability | CTO Mitigation Protocol |
| --- | --- | --- | --- | --- |
| 1. UPI Autopay / Bank Underwriting Delay | Payment aggregator risk teams require extended compliance reviews for digital asset merchant category codes (MCCs). | +1 to +3 Weeks | Medium | Dual-Gateway Strategy: Initiate parallel merchant applications with Cashfree, Decentro, and Razorpay in Week 2 rather than relying on a single provider. |
| 2. Apple Guideline 3.1.5 Crypto Queries | Apple Review Team issues temporary rejection demanding legal opinion letters, FIU proof, or non-custodial custody clarification. | +1 to +2 Weeks | High (First Review) | Pre-Packaged Compliance Kit: Upload FIU-IND certificate, video walkthrough of mandate creation, and demo credentials with test funds in initial review submission. |
| 3. CERT-In VAPT Audit Remediation Loop | Third-party penetration testing flags medium/high severity vulnerabilities in third-party npm packages, requiring code fixes & re-audit. | +1 to +2 Weeks | Medium-High | Pre-Audit SAST Scans: Run automated Snyk and SonarQube static scans in Sprint 4 to eliminate vulnerabilities before submitting to external auditor. |
| 4. Google Play 14-Day Tester Inactivity | If opted-in testers fail to open the app or drop below 20 active devices, Google Play algorithms reset the mandatory 14-day countdown. | +1 to +2 Weeks | Low-Medium | 75% Tester Buffer: Seed a dedicated cohort of 35+ verified testers (vs. 20 minimum) from Satmix WhatsApp community with daily push check-ins. |
| 5. Apple Org & D-U-N-S Verification | Dun & Bradstreet legal entity mismatch or delay in Apple Developer Organization account approval. | +1 to +2 Weeks | Low (If Done Early) | Immediate Week 1 Execution: Complete D-U-N-S matching and Apple Developer Organization verification immediately before writing Phase 1 code. |
| 6. Native SDK / Expo OS Compatibility | New iOS/Android OS patch introduces breaking changes in native camera/biometric/payment intent modules. | +3 to +5 Days | Low | Expo Config Plugins & Isolated Test Harness: Isolate third-party native SDKs behind TypeScript abstraction layers to swap modules without core refactoring. |

4. Scenario Analysis: Best-Case vs. Conservative vs. Delayed

To ensure complete alignment between engineering execution and CFO cash flow forecasting, the following table models the three release scenarios:

| Release Scenario | Total Duration | Primary Assumptions | CFO Runway Requirement |
| --- | --- | --- | --- |
| Best-Case Velocity | 10 Weeks (2.5 Months) | Instant UPI gateway approval, zero VAPT remediation re-tests, single-attempt Apple/Google store approvals. | ₹18.50 Lakhs (Lean Launch) |
| Conservative Baseline (Recommended) | 14 Weeks (3.5 Months) | Includes 1-week bank UAT buffer, 2-week VAPT audit & fix cycle, full 14-day Google Play cohort, and 1 Apple query cycle. | ₹23.87 Lakhs (Phase 1 Baseline Budget) |
| Worst-Case Delayed Horizon | 17 – 18 Weeks (4.5 Months) | Dual gateway underwriting delay (+3 wks) combined with Apple Guideline 3.1.5 secondary appeal cycle (+1 wk). | ₹31.50 Lakhs (Covered by 10% Contingency + M5 Hiring Deferral) |

5. Technical Definition of Done & Launch Gate Checklist

Visual & Interaction Polish: Flawless typography hierarchy, zero visual clipping on dynamic island/notch screens, and 60fps smooth charting gestures.

Penny-Accurate Compounding Math: Exact synchronization between CFO's dynamic asset allocation models and mobile compounding projection curves.

End-to-End UPI Autopay Reliability: 100% success rate on test e-mandate registration, pause, resume, and automated debit execution.

Verified e-KYC Compliance: Aadhaar XML and PAN real-time verification working with instant automated status updates.

CERT-In Security Certification: Zero high/critical vulnerabilities on both Android APK/AAB and iOS IPA builds.

Store Compliance Clearance: Full approval under Apple App Store Guideline 3.1.5 and Google Play Financial Services declarations.